# 90-day Growth Checklist

Filled with sample owners and dates aligned to the canvas.

## Weeks 0-2 – Align

| Task | Owner | Due date | Status | Notes |
| --- | --- | --- | --- | --- |
| Agree business goal and 3 KPIs | CEO / Head of Membership | 05 Nov | In progress | Definitions locked for the quarter |
| Baseline KPIs (8 weeks) | Data Lead | 06 Nov | Planned | Use cohort for renewals |
| Scope 10-day hygiene sprint | CRM Lead | 07 Nov | Planned | Contacts, membership, support |
| Name archetypes and RACI | PMO | 07 Nov | Planned | Publish in Teams |

## Weeks 3-4 – Prioritise

| Task | Owner | Due date | Status | Notes |
| --- | --- | --- | --- | --- |
| Select H1-H3 and write success criteria | Head of Membership | 14 Nov | Planned |  |
| Roadmap R1-R3 mapped to KPIs | PMO | 15 Nov | Planned |  |
| Adoption plan and job aids drafted | Training Lead | 15 Nov | Planned | 2-minute how-tos |
| Set weekly delivery review and dashboard | PMO | 15 Nov | Planned |  |

## Weeks 5-10 – Deliver

| Task | Owner | Due date | Status | Notes |
| --- | --- | --- | --- | --- |
| R1: Renewal friction fix live + demo | CRM Lead | 29 Nov | Planned | Auto-fill + value recap |
| R2: Onboarding emails + checklist live | Marketing Lead | 13 Dec | Planned | Segment by role |
| R3: Help answers widget live | Web Editor | 20 Dec | Planned | Top-20 topics |
| Run adoption and capture feedback | Training Lead | Weekly | Ongoing |  |
| Update KPI dashboard and learning log | Data Lead | Weekly | Ongoing |  |

## Weeks 11-12 - Prove and scale

| Task | Owner | Due date | Status | Notes |
| --- | --- | --- | --- | --- |
| Re-measure KPIs vs baseline | Data Lead | 05 Jan | Planned |  |
| Decide scale/pause/pivot for H1-H3 | CEO/Head of Membership | 06 Jan | Planned |  |
| Board one-page summary prepared | PMO | 07 Jan | Planned |  |
| Capture next-quarter hypotheses | All | 07 Jan | Planned |  |